## Sheet1
Sprint 3 Retrospective
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
The positive attitude and willingness to help among team members were fantastic and worked together to identify the best dataset and algorithm. | We learned that maintaining a balance between new features and technical debt is crucial for long-term stability. | We lacked clarity on the acceptance criteria for some user stories, resulting in misunderstandings during development. | We longed for more detailed sprint planning discussions to uncover potential risks and dependencies.
Clerk Authentication: Integrating Clerk for user authentication was smooth and provided a solid foundation for managing user sign-ins and sign-ups. | Learned about the nuances of setting up and configuring Clerk authentication within a Next.js environment, including understanding middleware and API keys. | The initial implementation lacked detailed error handling, particularly for authentication and component rendering issues. | User Experience: Longed for a more refined authentication experience, including smoother transitions between login and sign-up flows.
Homepage & Navbar Creation: The creation of the initial navigation bar using NextJS, Tailwind CSS was effective. | Gained experience with Next.js routing, page components, layout, common issues such as module imports and missing exports, and how to resolve them. | While the initial styling was completed, there might be inconsistencies or missing elements that need to be addressed in future sprints. Features for managing user profiles or settings were not yet implemented. | Looked forward to more polished UI elements and interactive features to enhance user engagement. Longed to integrate backend services for CRUD operations for financial data.