## Sheet1
Sprint Backlog sample template for AI Based Personal Finance Advisor (Detailed Estimate for current sprint 2)
ID |  | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Sprint 2 | User Authentication | Authentication | As a user, I want to securely access the website through cloud. | Must | Completed | 1. The user can register with a valid email and password. 2. User can log in with registered credentials. 3. Password reset functionality is secure and straightforward. | Secure password hashing and storage. Account lockout after multiple failed login attempts. | Response time for authentication actions should be less than 2 seconds. Password reset emails should be delivered within 5 minutes. | 5 days | 4 days
2 |  | Stock Selection | Stock Prediction | As a user, I want to select a country, stock exchange, and stock so that I can view specific stock data | Must | Ready for Dev | 1. User can successfully select a country, stock exchange, and stock from dropdown lists. | Implement dropdown menus for country, stock exchange, and stock. | Selection should be quick with no significant lag. | 5 days | 5 days
3 |  | Forecast Horizon | Performance | As a user, I want to adjust the forecast horizon to see predictions for different time ranges. | Must | In Testing | 1. Forecast horizon slider adjusts the number of forecasted days shown in the graph. | Implement an interactive slider for forecast horizon. | The slider should update the forecast graph in real-time without refreshing the page. | 3 days | 3 days
4 |  | Date Range Selection | Stock Prediction | As a user, I want to select a date range for historical data analysis so that I can control the period displayed. | Must | In Progress | 1. User can set start and end dates. | Implement a date picker for start and end dates. | The date picker should work smoothly and allow selecting past and future dates. | 4 days | 4 days
5 |  | Model Parameters | Stock Prediction | As a user, I want to fine-tune the parameters of the forecasting models to optimize the results. | Must | In Progress | 1. User can adjust parameters (e.g., alpha for smoothing models) and see immediate impact on the forecast. | Allow dynamic adjustment of model parameters and show real-time updates to the prediction graph. | Adjusting parameters should not cause significant performance issues. | 3 days | 3 days
[7 empty] | Assignee : Mrs. Vijayalakshmi V |  | Due date : 28/09/24