## Sheet1
Sprint 1 Retrospective
Liked | Learned | Lacked | Longed For
Share aspects of the sprint that you enjoyed or found particularly effective. | Discuss lessons learned, whether they are related to processes, technical aspects, or teamwork. | Identify areas where the team felt a lack of resources, support, or information. | Discuss any desires or expectations that the team had but were not met during the sprint.
The positive attitude and willingness to help among team members were fantastic and worked together to identify the best dataset and algorithm. | We learned that maintaining a balance between new features and technical debt is crucial for long-term stability. | We lacked clarity on the acceptance criteria for some user stories, resulting in misunderstandings during development. | We longed for more detailed sprint planning discussions to uncover potential risks and dependencies.
Improved communication and sharing of resources from past feedback were evident. | Improved tracking of task progress through new tools and methods, which helped address delays more effectively. | Insufficient time for training on new tools and methods introduced, affecting the pace of adoption and effective usage. | Access to advanced tools or plugins for automated testing to reduce manual review times and ensure accuracy.
Effective delegation allowed each member to focus on their expertise areas, streamlining workflow. | Improved handling of dependencies due to more proactive planning based on previous reviews. | Limited time for technical documentation refinement, impacting standardization. | Additional support in data access, especially for specific datasets that required authorization, to expedite processing.
Regular check-ins helped maintain alignment, with clearer progress updates. | Understood the value of early identification and prioritization of dependencies for smoother execution. | Limited access to a few external resources required for analysis, which slowed down part of the model implementation. | Clearer documentation guidelines for easier standardization, as team members worked on varied technical documents.